## Sheet1
| BFA_Q017 Franchisee Management (Catherine Harris) |  | Hrs to points | 2 |  |  | Daily Rate | 525
[7 empty] | Hrly Rate | 70
|  |  | Hrs | pts
Epic | Name | Description | Estimate | Estimate | Remaining | Requestor | Owner
Domain | Create FranchiseeList object |  | 4 | 2 | 0 | Pete | John
Domain | Create FranchiseeListStatus object |  | 4 | 2 | 1 | Pete | John
|  |  |  | 0 | 1 | Pete | Pete
Notifications | Create new notification/reminder app | Run every two weeks. Check if franchisor notification or reminder due, send them, update list | 7.5 | 4 | 3 | Pete | John
Notifications | Create notification/reminder task on server: bi-weekly |  | 1 | 1 | 2 | Pete | John
| Create admin plugin: Franchisors Notified List | Display franchisors as on admin member list screen. Searchable, filtered, ordered. Show only franchisors who still have notifications | 2 | 1 | 4 | Pete | Pete
Notifications | Upgrade to install Franchisors Notified plugin |  | 1 | 1 | 3 | Pete | John
|  |  |  | 0 | 4 | Pete | John
Franchisor updates | Confirmation: New confirm plugin to agree to franchisee updates | Modal popup once logged in? Redirect to page with confirm plugin on bool on record "AgreedToUpdateFranchisees". Unable to access other member area page until agreed Modal popup on Franchisee Register pages? | 2 | 1 | 2 | Pete | John
Franchisor updates | Franchisee list: | Filtering alphabetically, first name, last name | 2 | 1 | 1 | Pete | John
Franchisor updates | Franchisee list: | Colour coding based on latest Franchisee Notification / add key | 5 | 3 | 1 | Pete | John
Franchisor updates | Franchisee list: | Delete functionality: set as red 'deleted' Update APIEndpoint to set action to deleted / or undelete | 5 | 3 | 1 | Pete | John
Franchisor updates | Franchisee list: | Add clear instructions to page - Contnet plugin (bfa to do) | 0 | 0
Franchisor updates | Franchisee list: | button to confirm list - opens Modal with added/updated/deleted lists and confirm button. | 3.5 | 2
Franchisor updates | Franchisee list: | Once confirmed - email sent to Catherine | 1 | 1
Franchisor updates | Franchisee list: | Plugins in Core so need to sort way of quick editing/updating (inject js from web script as per core menu admin) | 1 | 1
0
Management Rules | Add Territories/Agreements owned to Franchisee form | Edtiable field - update site + update emails (with difference) | 4 | 2
Management Rules | Add validation | Email and Postcode combination validation | 3 | 2
Management Rules | New franchisee or update message | Empty first name/surname boxes if confirming a new franchisee | 0.5 | 0
0
Submission | Admin plugin: Franchisor Updates | List Franchisors (as per notifications) that have comfirmed - enable acception and grey out in list (able to 'unaccept'?) | 3.5 | 2
Submission | Admin plugin: Franchisor detail | List of changes to franchisees grouped by added, edited, deleted - enable acception and grey out in list (able to 'unaccept'?) | 3.5 | 2
Submission | Admin Plugin: Franchisor change detail | Show exactly what was added/changed/deleted down to field level - enable acception and grey out in list (able to 'unaccept'?) | 3.5 | 2
Submission | Changes submitted to site/CRM | Once changes accepted, update site and CRM. Add delete API push to CRM | 5 | 3
Submission | Rejection | Modal popup - accepts reason for rejection - email sent to Franchisor with reason (cc'd to support) | 2 | 1
0
Testing | Testing | Testing of all aspects | 9.5 | 5
0
Quote Mgt | Spec |  | 3 | 2
Quote Mgt | Quotation |  | 4 | 2
Release | Feedback/Snags/support |  | 3 | 2
Release | Releasing of project |  | 1 | 1
Testing
Proj Mgt
TOTAL |  |  | 84.5 |  |  |  | 5915